## Feature Map
IONIRIX SOVEREIGN UPDATE — FEATURE MAP
Feature ID | Deliverable | Module | Feature Name | Description | Priority | Phase | Week Target | Dependencies | Status | Acceptance Criteria
SWK-001 | Sovereign World Kernel | Tick Manager | Tick Manager Core | Core tick advancement engine that drives deterministic world simulation forward one tick at a time. | P0 Critical | 1 | Wk 1-2 | — | Not Started | Tick counter increments; world-state updates atomically per tick
SWK-002 | Sovereign World Kernel | Event Router | Event Router | Priority-based event classification and routing system with support for multi-channel dispatch. | P0 Critical | 1 | Wk 2-3 | SWK-001 | Not Started | Events classified by type/priority and routed to correct handlers within same tick
SWK-003 | Sovereign World Kernel | World-State Object | World-State Object | Authoritative, versioned, immutable-per-tick world-state container holding all simulation data. | P0 Critical | 1 | Wk 1-2 | — | Not Started | State is immutable within a tick; versioned snapshots accessible by tick number
SWK-004 | Sovereign World Kernel | Kernel Lifecycle | Kernel Lifecycle State Machine | State machine governing kernel transitions: Init→Load→Tick→Evaluate→Persist→Idle. | P0 Critical | 1 | Wk 2-3 | SWK-001; SWK-003 | Not Started | Kernel transitions through all states in correct order; invalid transitions rejected
SWK-005 | Sovereign World Kernel | Kernel Control API | Kernel Control API | External API exposing advance_tick, inject_event, spawn_agent, modify_environment, run_scenario, get_state_snapshot. | P0 Critical | 1 | Wk 3-4 | SWK-001; SWK-002; SWK-003; SWK-004 | Not Started | All 6 API endpoints callable and return correct responses
SWK-006 | Sovereign World Kernel | Agent Orchestrator | Agent Orchestrator | Full agent lifecycle manager handling spawn, execute, suspend, and terminate operations. | P0 Critical | 3 | Wk 9-10 | SWK-001; SWK-003; SWK-005 | Not Started | Agents spawn, execute actions, suspend, and terminate correctly across ticks
SWK-007 | Sovereign World Kernel | Anomaly Detector | Anomaly Detector | Pattern-matching engine that flags trajectory deviations and unexpected simulation behaviors. | P1 High | 3 | Wk 10-11 | SWK-003; SWK-006 | Not Started | Anomalies detected with <5% false positive rate on test scenarios
SWK-008 | Sovereign World Kernel | Kernel Query API | Kernel Query API | Read-only API: query_world_state, query_agent, query_timeline, query_anomalies. | P1 High | 3 | Wk 11-12 | SWK-003; SWK-006; SWK-007 | Not Started | All 4 query endpoints return correct filtered results
SWK-009 | Sovereign World Kernel | Tick Manager | Deterministic Tick Ordering | Deterministic ordering and scheduling of tick operations for reproducible simulation runs. | P0 Critical | 1 | Wk 1-2 | SWK-001 | Not Started | Same input produces identical tick sequence across runs
SWK-010 | Sovereign World Kernel | Event Router | Event Causality Chain Tracking | Tracks parent-child causality chains across events for full provenance tracing. | P1 High | 2 | Wk 5-6 | SWK-002 | Not Started | Each event references its causal parent; chain queryable end-to-end
SWK-011 | Sovereign World Kernel | Agent Orchestrator | Agent Compute Distribution | Distributes agent computation across available resources for parallel execution. | P2 Medium | 3 | Wk 11-12 | SWK-006 | Not Started | Agent workload distributes evenly; no single-thread bottleneck
SWK-012 | Sovereign World Kernel | Kernel Lifecycle | Kernel State Transition Guards | Validation guards preventing invalid state machine transitions with error reporting. | P1 High | 1 | Wk 3-4 | SWK-004 | Not Started | Invalid transitions raise descriptive errors; no silent failures
WSB-001 | World-State Bus | Schema Validator | Agent Schema Definition | Defines and validates the canonical schema for agent objects in the world-state bus. | P0 Critical | 2 | Wk 5-6 | SWK-003 | Not Started | Agent objects conform to schema; invalid agents rejected with error details
WSB-002 | World-State Bus | Schema Validator | Environment Schema Definition | Defines and validates the canonical schema for environment objects. | P0 Critical | 2 | Wk 5-6 | SWK-003 | Not Started | Environment objects conform to schema; invalid objects rejected
WSB-003 | World-State Bus | Schema Validator | Event Schema Definition | Defines and validates the canonical schema for event objects with type classification. | P0 Critical | 2 | Wk 5-6 | SWK-002 | Not Started | Event objects conform to schema; type field validated against enum
WSB-004 | World-State Bus | Schema Validator | Anomaly Schema Definition | Defines and validates the canonical schema for anomaly records. | P1 High | 2 | Wk 6-7 | SWK-007 | Not Started | Anomaly records conform to schema with severity and type fields validated
WSB-005 | World-State Bus | Schema Validator | Frame Schema Definition | Defines and validates the canonical schema for simulation frame objects. | P1 High | 2 | Wk 6-7 | SWK-003 | Not Started | Frame objects contain required fields; tick reference valid
WSB-006 | World-State Bus | Durable Object State Bridge | Durable Object State Bridge | Bridges Python simulation state to Cloudflare Durable Objects for edge-native persistence. | P0 Critical | 2 | Wk 6-8 | SWK-003; WSB-001; WSB-002; WSB-003 | Not Started | State writes from Python visible in DO within 100ms
WSB-007 | World-State Bus | WebSocket Subscription Mgr | WebSocket Subscription Model | Pub/sub WebSocket channels enabling real-time state streaming to connected clients. | P0 Critical | 2 | Wk 7-8 | WSB-006 | Not Started | Clients subscribe to channels and receive state updates within 50ms of write
WSB-008 | World-State Bus | WebSocket Subscription Mgr | Subscription Filtering | Granular subscription filters by agent ID, event type, region, and severity level. | P1 High | 2 | Wk 7-8 | WSB-007 | Not Started | Filtered subscriptions deliver only matching events; no false deliveries
WSB-009 | World-State Bus | Command Processor | Command Validation Pipeline | Five-stage command pipeline: Auth→Schema→Consistency→Execute→Acknowledge. | P0 Critical | 2 | Wk 7-8 | WSB-006; WSB-001; WSB-002; WSB-003 | Not Started | Commands pass all 5 stages; failures return stage-specific error codes
WSB-010 | World-State Bus | Command Processor | Command Audit Log | Append-only audit log for all commands with causality tracing metadata. | P1 High | 2 | Wk 8 | WSB-009; SWK-010 | Not Started | Every command logged with timestamp, actor, causality chain, and result
UI-001 | UI Overhaul | Design System | Sovereign Design System | Complete design system: glass panels, spectral cyan accents, sovereign paneling components. | P0 Critical | 4 | Wk 13-14 | — | Not Started | Design tokens, component library, and style guide documented and importable
UI-002 | UI Overhaul | Simulation Dashboard | Simulation Dashboard | Real-time world-state visualization showing live tick data, agent counts, and event feeds. | P0 Critical | 4 | Wk 13-15 | UI-001; WSB-007 | Not Started | Dashboard renders live simulation data with <100ms visual latency
UI-003 | UI Overhaul | Agent Density Renderer | Agent Density Maps | Spatial heatmap visualization with filtering by agent type, state, and activity level. | P1 High | 4 | Wk 14-15 | UI-001; UI-002; WSB-007 | Not Started | Heatmap renders 1000+ agents with interactive filtering
UI-004 | UI Overhaul | Timeline Scrubber | Timeline Scrubber | Tick-level timeline with event markers, drag-to-seek, and playback controls. | P1 High | 4 | Wk 14-15 | UI-001; UI-002; WSB-007 | Not Started | Scrubber navigates tick history; event markers clickable
UI-005 | UI Overhaul | Tick Inspector | Tick Inspector | Single-tick deep dive view showing all events, state changes, and anomalies for a given tick. | P1 High | 4 | Wk 15-16 | UI-001; UI-002; SWK-008 | Not Started | Inspector displays complete tick data with expandable event details
UI-006 | UI Overhaul | Scenario Builder | Scenario Builder | Variable controls, presets, and branch diff view for scenario experimentation. | P2 Medium | 4 | Wk 15-16 | UI-001; UI-002; SWK-005 | Not Started | User can create scenario, adjust variables, run, and compare diff
UI-007 | UI Overhaul | Simulation Dashboard | Zustand WebSocket Stores | Zustand state stores connected to WebSocket subscriptions for reactive UI updates. | P0 Critical | 4 | Wk 13-14 | WSB-007; UI-001 | Not Started | Zustand stores sync with WebSocket within 50ms; React re-renders on change
UI-008 | UI Overhaul | Agent Density Renderer | Canvas/WebGL Rendering | Canvas/WebGL rendering pipeline for high-performance heatmaps and density maps. | P2 Medium | 4 | Wk 15-16 | UI-003 | Not Started | WebGL renders 10,000+ data points at 60fps
UI-009 | UI Overhaul | Design System | Responsive Sovereign Paneling | Responsive grid system implementing sovereign paneling layout across screen sizes. | P1 High | 4 | Wk 13-14 | UI-001 | Not Started | Layout adapts correctly at 3 breakpoints: mobile, tablet, desktop
UI-010 | UI Overhaul | Simulation Dashboard | Anomaly Alert Strip | Real-time anomaly alert strip integrated into dashboard header for immediate visibility. | P1 High | 4 | Wk 15-16 | UI-002; SWK-007 | Not Started | Anomaly alerts appear within 1 tick of detection with severity color coding
CHT-001 | Chat Runtime | Chat Engine | Simulation-Aware Context Injection | Injects current tick, agent states, recent events, and anomalies into chat context window. | P0 Critical | 3 | Wk 9-10 | SWK-008; WSB-007 | Not Started | Chat responses reference current simulation state accurately
CHT-002 | Chat Runtime | Query Translator | NL to Structured Query | Translates natural language questions into structured world-state queries. | P0 Critical | 3 | Wk 10-11 | CHT-001; SWK-008 | Not Started | 80%+ of test NL queries produce correct structured queries
CHT-003 | Chat Runtime | Chat Engine | Agent Introspection | Deep inspection of individual agent state, memory, history, and decision traces. | P1 High | 3 | Wk 11-12 | CHT-001; SWK-006 | Not Started | Full agent state tree viewable with history navigation
CHT-004 | Chat Runtime | Chat Engine | Conversational Agent Interview | Interactive dialogue mode for interviewing simulation agents about their state and decisions. | P2 Medium | 3 | Wk 11-12 | CHT-003 | Not Started | Agent responds in-character with state-consistent answers
CHT-005 | Chat Runtime | Narrative Generator | Narrative Generation | Event-to-prose pipeline transforming simulation events into readable narratives. | P1 High | 6 | Wk 21-22 | CHT-001; SWK-008 | Not Started | Generated prose accurately reflects event sequence and outcomes
CHT-006 | Chat Runtime | Narrative Generator | Narrative Modes | Three distinct narrative styles: Chronicle (factual), Dramatic (literary), Analytical (data-driven). | P2 Medium | 6 | Wk 22-23 | CHT-005 | Not Started | Each mode produces stylistically distinct output for same events
CHT-007 | Chat Runtime | Chat Engine | Anomaly Explanation | Root cause analysis engine explaining why anomalies occurred with causal chain evidence. | P1 High | 6 | Wk 22-23 | SWK-007; SWK-010; CHT-001 | Not Started | Explanations reference correct causal events with confidence scores
CHT-008 | Chat Runtime | Chat Engine | Predictive Reasoning | Projects future simulation trajectories from current anomaly patterns. | P2 Medium | 6 | Wk 23-24 | CHT-007; SWK-007 | Not Started | Predictions include probability ranges and key inflection variables
PRS-001 | Persistence Layer | Snapshot Manager | World Snapshot Serialization | Serializes complete world-state at configurable tick intervals for persistence. | P0 Critical | 5 | Wk 17-18 | SWK-003 | Not Started | Snapshot captures full state; deserialized snapshot equals original
PRS-002 | Persistence Layer | Snapshot Manager | Snapshot Storage to R2 | Stores serialized snapshots to Cloudflare R2 with content-addressed naming. | P0 Critical | 5 | Wk 17-18 | PRS-001 | Not Started | Snapshots written to R2; retrievable by tick number or hash
PRS-003 | Persistence Layer | Snapshot Manager | Snapshot Index | Maintains index of all snapshots with tick number, timestamp, hash, and size metadata. | P1 High | 5 | Wk 18-19 | PRS-002 | Not Started | Index queryable by tick range; returns correct metadata for each snapshot
PRS-004 | Persistence Layer | Snapshot Manager | Agent Memory Persistence | Persists structured agent memory documents versioned per tick for full history. | P0 Critical | 5 | Wk 18-19 | SWK-006; PRS-001 | Not Started | Agent memory retrievable at any tick; version chain intact
PRS-005 | Persistence Layer | Event Log Service | Event Log System | Append-only event log with full causality chain references for audit and replay. | P0 Critical | 5 | Wk 18-19 | SWK-010; PRS-001 | Not Started | Events append-only; causality chains queryable; no mutations
PRS-006 | Persistence Layer | Event Log Service | Tiered Retention | Three-tier retention policy: hot (immediate), warm (recent), cold (archived) storage. | P1 High | 5 | Wk 19-20 | PRS-005 | Not Started | Data migrates between tiers on schedule; cold data retrievable within 5s
PRS-007 | Persistence Layer | Rollback Controller | Point-in-Time Rollback | Restores world-state to any previously persisted snapshot with full fidelity. | P0 Critical | 5 | Wk 19-20 | PRS-001; PRS-002; PRS-004; PRS-005 | Not Started | Rollback to tick N produces identical state to original tick N snapshot
PRS-008 | Persistence Layer | Rollback Controller | Timeline Branching | Creates new timeline branches on rollback for parallel universe exploration. | P1 High | 5 | Wk 19-20 | PRS-007 | Not Started | Branch created on rollback; both timelines advance independently
PRS-009 | Persistence Layer | Rollback Controller | Cross-Mode Continuity | State migration across simulation modes: Planetary → Cosmic → Multiverse. | P2 Medium | 5 | Wk 20 | PRS-001; PRS-007 | Not Started | State transfers between modes with validated schema mapping

## Module Registry
MODULE REGISTRY — IONIRIX SOVEREIGN UPDATE
Module ID | Module Name | Language / Runtime | Deliverable | Responsibility | Dependencies | Interfaces (APIs Exposed) | Data Stores Used
MOD-001 | Tick Manager | Python | Sovereign World Kernel | Core simulation clock that advances world-state one tick at a time. Manages deterministic ordering, scheduling priority, and tick lifecycle hooks. | — | advance_tick(), get_tick(), schedule_action() | In-memory tick counter; World-State Object
MOD-002 | Event Router | Python | Sovereign World Kernel | Classifies incoming events by type and priority, routes them to registered handlers, and maintains causality chain references. | MOD-001 | route_event(), classify_event(), get_causality_chain() | Event queue; Causality index
MOD-003 | World-State Object | Python | Sovereign World Kernel | Authoritative container for all simulation state. Immutable within a tick, versioned per tick, supports snapshot export. | MOD-001 | get_state(), get_snapshot(), diff_states() | Versioned state store (in-memory)
MOD-004 | Agent Orchestrator | Python | Sovereign World Kernel | Manages full agent lifecycle: spawn, execute, suspend, terminate. Distributes agent compute and tracks agent state transitions. | MOD-001; MOD-003 | spawn_agent(), execute_agent(), suspend_agent(), terminate_agent() | Agent registry; World-State Object
MOD-005 | Anomaly Detector | Python | Sovereign World Kernel | Pattern-matching engine scanning simulation trajectories for deviations. Flags anomalies with severity, type, and causal context. | MOD-003; MOD-004 | detect_anomalies(), get_anomalies(), configure_thresholds() | Anomaly log; Pattern rule store
MOD-006 | Durable Object State Bridge | TypeScript (CF Workers) | World-State Bus | Bridges Python simulation state writes to Cloudflare Durable Objects for edge-native persistence and real-time client access. | MOD-003; MOD-007 | write_state(), read_state(), sync_state() | Cloudflare Durable Objects
MOD-007 | Schema Validator | TypeScript | World-State Bus | Validates all world-state objects (agents, environments, events, anomalies, frames) against canonical JSON schemas. | — | validate(), get_schema(), register_schema() | Schema definition store
MOD-008 | WebSocket Subscription Manager | TypeScript (CF Workers) | World-State Bus | Manages pub/sub WebSocket channels with subscription filtering by agent ID, event type, region, and severity. | MOD-006 | subscribe(), unsubscribe(), publish(), filter() | Subscription registry; Durable Objects
MOD-009 | Command Processor | TypeScript (CF Workers) | World-State Bus | Five-stage command pipeline (Auth→Schema→Consistency→Execute→Acknowledge) with audit logging and causality tracing. | MOD-006; MOD-007 | process_command(), validate_command(), get_audit_log() | Command audit log; Durable Objects
MOD-010 | Simulation Dashboard | TypeScript (React) | UI Overhaul | Primary visualization surface showing real-time tick data, agent counts, event feeds, and anomaly alerts. | MOD-008; UI-001 | Dashboard React component; Zustand store bindings | Zustand stores (WebSocket-fed)
MOD-011 | Agent Density Renderer | TypeScript (React + WebGL) | UI Overhaul | WebGL-accelerated spatial heatmap renderer for agent density visualization with interactive filtering controls. | MOD-010 | DensityMap React component; filter API | Zustand agent store
MOD-012 | Timeline Scrubber | TypeScript (React) | UI Overhaul | Tick-level timeline component with event markers, drag-to-seek navigation, and playback speed controls. | MOD-010 | TimelineScrubber React component; seek API | Zustand timeline store
MOD-013 | Tick Inspector | TypeScript (React) | UI Overhaul | Deep-dive view for a single tick showing all events, state changes, anomalies, and agent actions. | MOD-010 | TickInspector React component | Zustand tick detail store
MOD-014 | Scenario Builder | TypeScript (React) | UI Overhaul | Variable control panel with presets, scenario execution, and branch diff comparison view. | MOD-010 | ScenarioBuilder React component; preset API | Zustand scenario store
MOD-015 | Chat Engine | TypeScript (CF Workers) | Chat Runtime | Core chat runtime with simulation-aware context injection, agent introspection, and anomaly explanation. | MOD-008; MOD-004; MOD-005 | send_message(), get_context(), introspect_agent() | Chat session store; World-State (read)
MOD-016 | Query Translator | TypeScript | Chat Runtime | Translates natural language questions into structured world-state queries using LLM-based parsing. | MOD-015 | translate_query(), parse_nl() | Query template cache
MOD-017 | Narrative Generator | TypeScript | Chat Runtime | Transforms simulation events into readable prose using Chronicle, Dramatic, and Analytical narrative modes. | MOD-015; MOD-002 | generate_narrative(), set_mode() | Event log (read); Narrative template store
MOD-018 | Snapshot Manager | TypeScript (CF Workers) | Persistence Layer | Handles world snapshot serialization, R2 storage, snapshot indexing, and agent memory persistence. | MOD-003; MOD-006 | create_snapshot(), get_snapshot(), list_snapshots() | Cloudflare R2; Snapshot index
MOD-019 | Event Log Service | TypeScript (CF Workers) | Persistence Layer | Append-only event log with tiered retention (hot/warm/cold) and causality chain queryability. | MOD-002; MOD-006 | append_event(), query_events(), migrate_tier() | Cloudflare R2; Durable Objects
MOD-020 | Rollback Controller | TypeScript (CF Workers) | Persistence Layer | Point-in-time rollback engine with timeline branching and cross-mode continuity support. | MOD-018; MOD-019 | rollback_to(), create_branch(), migrate_mode() | Snapshot index; R2; Durable Objects

## Milestone Tracker
MILESTONE TRACKER — IONIRIX SOVEREIGN UPDATE
Milestone ID | Phase | Phase Name | Week Range | Milestone Description | Key Deliverables | Acceptance Gate | Status | Risk Level | Risk Notes
MS-001 | 1 | Foundation | Weeks 1-4 | Kernel can advance ticks and route events with deterministic state | Tick Manager; Event Router; World-State Object; Kernel Control API; Kernel lifecycle state machine | Integration test passes — 1,000 ticks with deterministic output | Not Started | Low | —
MS-002 | 2 | Integration | Weeks 5-8 | Python sim writes state, TS runtime reads in real-time | Durable Object bridge; Schema validation; WebSocket subscriptions; Command layer; Python↔TS integration | End-to-end state sync test — Python writes, TS reads within 100ms | Not Started | Medium | Durable Object performance under load needs early validation
MS-003 | 3 | Intelligence | Weeks 9-12 | Agents run, anomalies detect, chat queries the world | Agent Orchestrator; Anomaly Detector; Chat runtime; Query engine; Agent introspection | 100-agent simulation with anomaly detection and chat query response | Not Started | Medium | Agent compute distribution and anomaly false-positive tuning may require iteration
MS-004 | 4 | Interface | Weeks 13-16 | Full visual simulation control and monitoring | Sovereign UI design system; Dashboard; Agent density maps; Timeline scrubber; Tick inspector; Scenario builder | All 5 core views render live simulation data with <100ms latency | Not Started | Low | —
MS-005 | 5 | Persistence & Scale | Weeks 17-20 | Full persistence, rollback, and mode transitions | World snapshots; Agent memory persistence; Event logs; Point-in-time rollback; Cross-mode continuity | Rollback to tick N and resume with identical state verified | Not Started | High | Cross-mode continuity (Planetary→Cosmic→Multiverse) is architecturally novel and untested
MS-006 | 6 | Polish & Docs | Weeks 21-24 | Production-ready sovereign world engine with complete documentation | Narrative engine; Anomaly reasoning; Architecture diagrams; Release notes; Feature map; Investor summary | Documentation review complete; all P0 features shipped and passing tests | Not Started | Low | —

## Release Notes
IONIRIX SOVEREIGN UPDATE — RELEASE NOTES v2.0
Category | Item | Description
NEW | Sovereign World Kernel | Authoritative, tick-based world engine with deterministic state management and reproducible simulation runs.
NEW | World-State Bus | Real-time Python↔TypeScript state bridge via Cloudflare Durable Objects with schema validation and pub/sub channels.
NEW | Event Router | Priority-based event classification and routing with full causality chain tracking across ticks.
NEW | Agent Orchestrator | Full agent lifecycle management (spawn, execute, suspend, terminate) with compute distribution.
NEW | Anomaly Detector | Pattern-matching engine for simulation trajectory deviations with configurable thresholds and severity levels.
NEW | Simulation Dashboard | Real-time world-state visualization with sovereign-industrial design and live tick/agent/event feeds.
NEW | Agent Density Maps | Spatial heatmap with interactive filtering by agent type, state, and activity level via WebGL rendering.
NEW | Timeline Scrubber | Tick-level timeline with event markers, drag-to-seek navigation, and playback speed controls.
NEW | Tick Inspector | Single-tick deep dive showing all events, state changes, anomalies, and agent actions for any tick.
NEW | Scenario Builder | Variable controls, presets, scenario execution, and branch diff comparison for experimentation.
NEW | Simulation-Aware Chat | Chat runtime with real-time world-state context injection including tick, agents, events, and anomalies.
NEW | World-State Queries | Natural language to structured simulation query translation for intuitive data exploration.
NEW | Agent Introspection | Deep inspection of agent state, memory, history, and decision traces with conversational interview mode.
NEW | Narrative Generation | Event-to-prose pipeline with three modes: Chronicle (factual), Dramatic (literary), and Analytical (data-driven).
NEW | Anomaly Explanation | Root cause analysis engine with causal chain evidence and predictive trajectory reasoning.
NEW | World Snapshots | Configurable state serialization to Cloudflare R2 with content-addressed naming and snapshot indexing.
NEW | Agent Memory Persistence | Tick-versioned structured memory documents with full history retrieval at any point in time.
NEW | Event Log System | Append-only event logs with causality chains and tiered retention (hot/warm/cold storage).
NEW | Rollback System | Point-in-time rollback to any snapshot with automatic timeline branching for parallel exploration.
NEW | Cross-Mode Continuity | State migration across simulation modes: Planetary → Cosmic → Multiverse with validated schema mapping.
UPGRADED | UI Design System | Sovereign-industrial aesthetic with glass panels, spectral cyan accents, and responsive sovereign paneling grid.
UPGRADED | Chat Runtime | Evolved from standalone chat to simulation-aware runtime with command capabilities and world-state context.
ARCHITECTURE | Deterministic Tick Model | Reproducible simulation runs enabling branching, rollback, and diff comparison across timelines.
ARCHITECTURE | Edge-Native Deployment | Built on Cloudflare global network using Workers, Durable Objects, and R2 for worldwide low-latency access.
ARCHITECTURE | Event-Sourced Persistence | Full event sourcing with append-only logs, causality chains, and point-in-time state reconstruction.

## Risk Register
RISK REGISTER — IONIRIX SOVEREIGN UPDATE
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Owner | Status
RSK-001 | Technical | Durable Object performance under high-frequency tick writes may degrade at scale | Medium | High | 6 | Benchmark early in Phase 2; implement write batching; fallback to Redis read replicas if DO throughput insufficient | Lead Engineer | Open
RSK-002 | Technical | WebSocket hibernation reconnection edge cases causing missed state updates | Low | Medium | 2 | Implement reconnection protocol with state reconciliation; automated reconnection tests in CI | Lead Engineer | Open
RSK-003 | Technical | Python↔TypeScript serialization overhead introducing tick latency above target thresholds | Medium | Medium | 4 | Use MessagePack or Protocol Buffers instead of JSON; benchmark serialization in Phase 2 integration tests | Lead Engineer | Open
RSK-004 | Technical | Cross-mode continuity state migration complexity exceeding design assumptions | High | High | 9 | Prototype mode transition in Phase 3; define strict mode transition protocol with schema mapping validation | Lead Engineer | Open
RSK-005 | Schedule | UI overhaul scope exceeds Phase 4 four-week window due to design iteration | Medium | Medium | 4 | Prioritize P0 views first (Dashboard, Zustand stores); P2/P3 features (Scenario Builder, WebGL) can shift to Phase 6 | Lead Engineer | Open
RSK-006 | Technical | Anomaly detector false positive rate reducing signal quality and user trust | Medium | Low | 2 | Configurable detection thresholds; user feedback loop for false positive reporting; threshold tuning in Phase 3 | Lead Engineer | Open
RSK-007 | Technical | Deterministic tick reproducibility breaks across Python versions or OS environments | Low | High | 3 | Pin Python version in runtime config; seed all RNG sources; snapshot validation tests comparing outputs across environments | Lead Engineer | Open
RSK-008 | Resource | Single-developer bandwidth insufficient for 24-week timeline across all deliverables | High | High | 9 | Phase-gate milestones with explicit go/no-go decisions; scope reduction triggers at each gate; P2/P3 features deprioritized if behind | Project Lead | Open
RSK-009 | External | Cloudflare Durable Objects API changes or deprecations during development cycle | Low | Medium | 2 | Abstract all DO interactions behind adapter layer; pin CF Worker runtime version; monitor CF changelog | Lead Engineer | Open
RSK-010 | Technical | Chat runtime latency exceeds acceptable thresholds when injecting full world-state context | Medium | Medium | 4 | Context windowing — inject only relevant state slice; lazy-load secondary context on follow-up queries; cache recent context | Lead Engineer | Open